## Project Plan - Revised
Task ID | Description | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
Phase 1
1 | Onboarding and Requirement Gathering | bar: W0
1.1 | Onboarding of CT team in ADCCI's infra and getting all the necessary accesses resolved | bar: W0
1.2 | Conducting sizing activity for Production, Development and Testing​ | bar: W1
1.3 | Restructing and providing a approach for ETL ingestion and processing framework based on discovery​ | bar: W1
1.4 | Defining business glossary alongside BUs and Identifying and modeling RBAC​ | bar: W1
1.5 | Document data cleansing techniques, such as outlier detection, data deduplication, and data standardization procedures.​ | bar: W1
1.6 | Define Unit testing strategy, User acceptance testing use-cases, analysis of success criteria and code acceptance parameters​ | bar: W1
1.7 | Documenting the findings and observations and Re-Defining the technical scope of work, if any change arise​ | bar: W1
2 | Technical Discovery & Infrastructure Planning | bar: W1 to W2
2.1 | Gap Analysis, Design & Roadmap | bar: W1 to W2
2.1.1 | Assessment of the current system at ADCCI | bar: W1 to W2
2.1.2 | Details Level Assessment, Identify gaps, issues and challenges related to network security, identity and access management, Governance and Compiance, Tagging and Naming Convention | bar: W1 to W2
2.1.3 | Discussion on Network Requirements and Connectivity Architecture | bar: W1 to W2
2.1.4 | Proposing a future state roadmap covering the data analytics journey for the organization and advance analytics use cases for further phase releases | bar: W1 to W2
2.1.5 | Detailing out the architecture, technology landscape assessment report and recommendation | bar: W1 to W2
2.1.6 | Implementation roadmap including implementation services, resource requirements, and timelines etc. | bar: W1 to W2
2.1.7 | Develop a migration plan and cut-over strategy, ensuring a smooth transition.​ | bar: W1 to W2
2.1.8 | Subscription Level Access | bar: W1 to W2
2.1.9 | Update Requirements and Design Document | bar: W1 to W2
2.1.10 | Solution Design Review And Sign-off | bar: W1 to W2
3 | Infrastructure Implementation- Develop And Deploy | bar: W3 to W9
3.1 | Hub (Centralized) Infrastructure setup | bar: W3
3.1.1 | Creation of Private DNS Zones | bar: W3
3.1.2 | Setup the peering between hub and Transit virtual network | bar: W3
3.1.3 | Creation and configuration of Microsoft Purview | bar: W3
3.1.4 | Setup Purview SHIR VM and Azure Key Vault for Purview | bar: W3
3.1.5 | Creation and configuration of private endpoints for Microsoft Purview and Key Vault | bar: W3
3.2 | Spoke Dev Resource Deployment | bar: W3 to W9
[5 empty] | DEV |  | UAT |  | PROD
3.2.1 | Procure IP address CIDR block tailored for spoke virtual network | bar: W3; W5; W7
3.2.2 | Creation of the resource group | bar: W3; W5; W7
3.2.3 | Deployment and Configuration of the required networking components for the enviornment | bar: W3; W5; W7
3.2.4 | Deployment and Configuration of the required Azure PaaS services for the environment | bar: W3; W5; W7
3.2.5 | Deployment and Configuration of the private endpoint for all the azure paas services | bar: W3; W5; W7
3.2.6 | Creation of A records in Private DNS Zones in centralized location (Hub) | bar: W3; W5; W7
3.2.7 | Configuration of SHIR, SHA VM, Onprem Data Gateway and installation of required softwares | bar: W3; W5; W7
3.2.8 | Assign RBAC roles to groups or users for specific resources | bar: W3; W5; W7
3.2.9 | Creation of connections for the data source in Microsoft Fabric | bar: W3 to W8
3.2.10 | Setting up of Logging and Monitoring - Diagnostic Settings, Resource Health Alerts, Metric Alerts | bar: W3 to W8
3.2.11 | Sanity Testing of the complete environment | bar: W4; W6; W8
3.2.12 | Enable Microsoft defender for continuous monitoring, threat detection, and security recommendations | bar: W8 to W9
4 | Data Platform Enablement | bar: W4 to W10
4.1 | Data Integration, Processing & Storage (ETL/ELT) | bar: W4 to W9
4.1.1 | Establish Data ingestion metadata driven Pipeline/Framework for batch and incremental load data sources.​ | bar: W4 to W9
4.1.2 | Design mechanisms for loading processed data into the target data storage systems for Batch load and implementing incremental/delta load.​ | bar: W4 to W7
4.1.3 | Developing Event hubs streams for streaming/near to real time data load while incorporating incremental/delta load logic on data streaming pipelines​ | bar: W4 to W6
4.1.4 | Enable connections to Oracle, on-premises DB, cloud DB, API, JSON, streaming, FTP, MS Dynamics. & real-time sources | bar: W7 to W9
4.1.5 | Defining SCD and CDC as per data requirements​ | bar: W7
4.1.6 | Design transformation logic to cleanse, validate, enrich, and aggregate data according to business requirements for data marts | bar: W7 to W9
4.2 | Data Quality and Validation | bar: W6 to W9
4.3 | Implementing the identified DQ rules, contraints, parameters and creating DQ and validation framework. | bar: W6 to W9
4.4 | Creating the necessary schema and one view table | bar: W6
4.5 | Working with sample table and synthetic data for testing the framework with wrong values | bar: W6 to W9
4.6 | Implementing error handling and notification rules | bar: W7 to W9
4.7 | Orchestrating the DQ framework by refactoring the pipelines | bar: W7 to W9
4.3 | Data Management & Warehousing | bar: W7 to W12
4.3.1 | Develop a migration plan and cut-over strategy, ensuring a smooth transition.​ | bar: W7 to W12
4.3.2 | Develop appropriate data models, ETL pipelines, data marts, and data lakes.​ | bar: W7 to W12
4.3.3 | Design transformation logic to cleanse, validate, enrich, and aggregate data according to business requirements for data marts | bar: W7 to W12
4.3.4 | Ensure scalable storage capacity, easy-to-use data import/export features, data compression and encryption, access controls, audit trails. | bar: W7 to W12
4.3.5 | Ensuring data readiness to be consumed by data scientist and visualization experts . | bar: W7 to W12
4.3.6 | Conduct initial data validation from the old architecture to the new post-migration.​ | bar: W7 to W12
4.3.7 | Implement a data migration approach with a parallel run and validate the migrated data. | bar: W7 to W12
4.3.8 | Implementing fabric best practices for the development model​ | bar: W11 to W12
4.4 | Data Governance (Data Cataloging, Profiling, Glossary) | bar: W4 to W7
4.4.1 | Identify attribute definitions, entity relationships | bar: W4 to W5
4.4.3 | Import glossary, create relationships within metadata and Associate glossary to metadata information | bar: W4 to W5
4.4.4 | Cataloging Metadata and Establishing a centralized repository or catalog serves as a single source of truth, where all metadata is stored and managed is essential. ​ | bar: W4 to W5
4.4.5 | Deploy robust data encryption algorithms and access control mechanisms to safeguard sensitive information. | bar: W4 to W5
4.4.6 | Implementing enterprise data catalog, data governance, data security policies and access control matrix.​ | bar: W4 to W5
4.4.7 | Include features for data lineage, audit trails, and metadata management.​ | bar: W4 to W5
4.4.8 | Create and run historical scans to discover metadata information in Azure Purview | bar: W5 to W7
4.4.9 | Building associations, relationships, defining collections and curating the scanning results | bar: W5 to W7
4.4.10 | Classifying data assets based on their sensitivity level, business criticality, and regulatory compliance requirements. | bar: W5 to W7
4.4.11 | Regularly updating metadata, refreshing data assets, and retiring obsolete data assets ensure that the catalog remains accurate and up-to-date. | bar: W5 to W7
5 | Azure DevOps Setup
5.1 | Creation of Azure DevOps Organization in a specific region | bar: W5
5.2 | Creation of Project and groups inside organization | bar: W5
5.3 | Initializing Repository inside Azure DevOps | bar: W5
5.4 | Configure Self-Hosted Agent in a Virtual Machine with required dependencies | bar: W5
5.5 | Installation of the required extension within the DevOps Portal for CI/CD utilization | bar: W5
6 | Azure Data Factory CI/CD | bar: W6 to W9
6.1 | Configuring service connection in Azure DevOps | bar: W6
6.2 | Attaching repository to ADF and commiting changes done by the developers. | bar: W6
6.3 | Configuring Ternary ADF for the deployment of SHIR if required | bar: W6 to W7
6.4 | Create Release pipeline for UATand PROD Envs | bar: W6 to W8
6.5 | Define deployment tasks inside release pipeline | bar: W7 to W8
6.6 | Configure override parameters for every linked services | bar: W7 to W8
6.7 | Configure pre-deployment approvals and post-deployment approvals | bar: W8
6.8 | Configure continuous deployment trigger | bar: W8
6.9 | Maintain and Running CICD Pipeline | bar: W8 to W14
7 | Power BI Report Wireframe, Development | bar: W7 to W13
7.1 | Define & Document key performance indicators (KPIs) and metrics for tracking to relevant data sources.​ | bar: W7 to W8
7.2 | Design wireframes in Figma/Power BI containing dummy data. | bar: W7 to W8
7.3 | Key performance indicators (KPIs) & Wire frame sign off | bar: W8 to W9
7.4 | Establish connectivity between Power BI desktop & Data Sources for development | bar: W9 to W10
7.5 | Implement Power Query transformations within Power BI for transforming data in required format if necessary | bar: W10
7.6 | Design a data model that organizes and structures the data for efficient querying and analysis. | bar: W10 to W11
7.7 | Implement any necessary calculations or business logic within the reports using DAX (Data Analysis Expressions) | bar: W10 to W12
7.8 | Develop Power BI Reports Visualization | bar: W11 to W12
7.9 | Additional Feature Implementation such as RLS | bar: W12 to W13
7.1 | Publishing the report on Power BI service | bar: W12 to W13
7.11 | Data Validation with use cases | bar: W12 to W13
8 | PowerBI CI/CD | bar: W9 to W14
8.1 | Identify the data Sources to be parameterised | bar: W9
8.2 | Create app registration using Azure AD | bar: W9
8.3 | Grant permission to app inside PowerBI workspace | bar: W9 to W10
8.4 | Create Build and release pipeline for UAT and PROD Workspaces | bar: W9 to W12
8.5 | Cleaning up the artifact | bar: W10 to W12
8.6 | Updating release pipeline security to define access | bar: W11 to W12
8.7 | Configure pre-deployment approvals and post-deployment approvals | bar: W11 to W12
8.8 | Configure continuous deployment trigger | bar: W12
8.9 | Maintain and Running CICD Pipeline | bar: W12 to W14
9 | SIT, UAT and Feedback Implementation | bar: W13 to W14
9.1 | SIT & Validation | bar: W13
9.2 | End to End process testing, sanity testing, model testing | bar: W12 to W14
9.3 | UAT Release & Feedback Implementation | bar: W13
9.4 | UAT Sign-Off | bar: W13 to W14
10 | User Training, Documentation and Go-Live | bar: W13 to W14
10.1 | User Training and Documentation | bar: W13 to W14
10.2 | Documentation Sign-Off | bar: W13 to W14
10.3 | Go-Live | bar: W13 to W14

## Resource Matrix - Revised
Sr No | Resources | Count | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | Total Hours
1 | Project Manager | 1 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 280
2 | Business Analyst | 1 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 140
3 | Infra Architect | 1 | 0 | 20 | 20 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
4 | Cloud Engineer | 1 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 10 | 10 | 10 | 10 | 10 | 410
5 | Network x Security Engineer | 1 | 0 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 40 | 40 | 20 | 10 | 10 | 10 | 10 | 360
6 | Data Architect | 1 | 0 | 20 | 20 | 20 | 20 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 130
8 | Data Engineering | 2 | 0 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 10 | 980
9 | Data Integration Engineer | 2 | 0 | 10 | 10 | 10 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380
10 | Sr Data Engineer | 1 | 0 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 240
11 | Data Governance Engineer | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 20 | 20 | 0 | 0 | 0 | 0 | 200
12 | Power BI Developer | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 340
13 | DevOps Engineer | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 40 | 40 | 40 | 20 | 10 | 10 | 5 | 5 | 5 | 185
Total |  | 14 | 0 | 190 | 210 | 200 | 230 | 265 | 285 | 315 | 295 | 255 | 195 | 165 | 160 | 140 | 130 | 3715

## Project Plan (hidden)
Task ID | Description | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
1 | Onboarding and Requirement Gathering | bar: W0
1.1 | Onboarding of CT team in ADCCI's infra and getting all the necessary accesses resolved | bar: W0
1.2 | Conducting sizing activity for Production, Development and Testing​ | bar: W1
1.3 | Restructing and providing a approach for ETL ingestion and processing framework based on discovery​ | bar: W1
1.4 | Defining business glossary alongside BUs and Identifying and modeling RBAC​ | bar: W1
1.5 | Confirming the naming/coding standards to be followed in ADCCI's environment​ | bar: W1
1.6 | Define Unit testing strategy, User acceptance testing use-cases, analysis of success criteria and code acceptance parameters​ | bar: W1
1.7 | Documenting the findings and observations and Re-Defining the technical scope of work, if any change arise​ | bar: W1
2 | Subscription Assessment and Optimal Changes | bar: W1
2.1 | Details Level Assessment, Identify gaps, issues and challenges related to network security, identity and access management, Governance and Compiance, Tagging and Naming Convention | bar: W1 to W2
2 | Technical Discovery & Infrastructure Planning | bar: W3
2.1 | Gap Analysis And Design | bar: W3 to W4
2.1.1 | Architecture Design And Review | bar: W3 to W4
2.1.2 | Discussion on Network Requirements and Connectivity Architecture | bar: W3 to W4
2.1.3 | Subscription Level Access | bar: W3 to W4
2.1.4 | Update Requirements and Design Document | bar: W3 to W4
2.1.5 | Solution Design Review And Sign-off | bar: W3 to W4
3 | Infrastructure Implementation- Develop And Deploy | bar: W4 to W10
3.1 | Hub (Centralized) Infrastructure setup | bar: W4
3.1.1 | Creation of Private DNS Zones | bar: W4
3.1.2 | Setup the peering between hub and Transit virtual network | bar: W4
3.1.3 | Creation and configuration of Microsoft Purview | bar: W4
3.1.4 | Setup Purview SHIR VM and Azure Key Vault for Purview | bar: W4
3.1.5 | Creation and configuration of private endpoints for Microsoft Purview and Key Vault | bar: W4
3.2 | Spoke Dev Resource Deployment | bar: W4 to W10
[6 empty] | DEV |  | UAT |  | PROD
3.2.1 | Procure IP address CIDR block tailored for spoke virtual network | bar: W4; W6; W8
3.2.2 | Creation of the resource group | bar: W4; W6; W8
3.2.3 | Deployment and Configuration of the required networking components for the enviornment | bar: W4; W6; W8
3.2.4 | Deployment and Configuration of the required Azure PaaS services for the environment | bar: W4; W6; W8
3.2.5 | Deployment and Configuration of the private endpoint for all the azure paas services | bar: W4; W6; W8
3.2.6 | Creation of A records in Private DNS Zones in centralized location (Hub) | bar: W4; W6; W8
3.2.7 | Configuration of SHIR, SHA VM, Onprem Data Gateway and installation of required softwares | bar: W4; W6; W8
3.2.8 | Assign RBAC roles to groups or users for specific resources | bar: W4; W6; W8
3.2.9 | Creation of connections for the data source in Microsoft Fabric | bar: W4 to W9
3.2.10 | Setting up of Logging and Monitoring - Diagnostic Settings, Resource Health Alerts, Metric Alerts | bar: W4 to W9
3.2.11 | Sanity Testing of the complete environment | bar: W5; W7; W9
3.2.12 | Enable Microsoft defender for continuous monitoring, threat detection, and security recommendations | bar: W9 to W10
4 | Data Science & Analytics
9.1 | Data Extraction & Storing
9.1.1 | Define data extraction requirements and extract relevant data points.
9.1.2 | Extracting Text Using Azure Document Intelligence.
9.2.3 | Translate Arabic text to English and vice-versa
9.2 | Enrich Data & Enable Search
9.2.1 | Create chunks for the text data
9.2.2 | Index data in Azure AI Search with the specified fields
9.2.3 | Create and Store Embeddings
9.2.4 | Create, train & update Indexer
9.3 | OpenAI integration for Knowledge Mining, RFP Generation & Evaluation
9.3.1 | OpenAI integration for Knowledge Mining, RFP Generation & Evaluation
9.3.2 | Prompt creation and optimization for chatbot enhancements, Knowledge Mining, RFP Generation & Evaluation
9.3.3 | Knowledge-mining implementation
9.3.4 | Model fine tuning for RFP generation for specified sections
9.3.5 | RFP generation in specified format
9.3.6 | RFP editing and saving
9.3.7 | Pre-Tender Clarification: Use of OpenAI model for answering questions from RFP
9.3.8 | Post-Tender Clarification: Prompt creation for analyzing the gap between submitted proposal and RFP
9.3.9 | Proposal Evaluation & Rating
9.3.10 | GAP analysis & implementation
9.3.11 | Report Generation
9.4 | Backend API Development
9.4.1 | Inference pipeline creation for QnA, RFP Generation and Evaluation
9.4.2 | Deployment & API Integration
9.4.3 | Inference pipeline integration and testing with UI
5 | Data Integration and Ingestion | bar: W5 to W8
Integrate with existing systems and data sources while maintaining current integrations without disruption.​ | bar: W5
Establish Data ingestion metadata driven Pipeline/Framework for batch and incremental load data sources.​ | bar: W5 to W8
Gather historical data for identified indicators over a specific time period.​ | bar: W5 to W6
Design mechanisms for loading processed data into the target data storage systems for Batch load and implementing incremental/delta load.​ | bar: W5
Developing streams for streaming/near to real time data load while incorporating incremental/delta load logic on data streaming pipelines .​ | bar: W6 to W8
Organize and maintain a comprehensive database of identified data.​ | bar: W6
Support integration with multiple data sources, including cloud and on-premises systems and real-time applications.​ | bar: W6 to W8
Enable connections to Oracle, on-premises DB, cloud DB, API, JSON, streaming, FTP, MS Dynamics.​ | bar: W7 to W8
Support CDC capabilities, built-in data mapping and transformation tools, real-time and batch integration | bar: W7 to W8
6 | Data Management and Storage | bar: W7 to W8
10.1 | Map source data elements to target data structures, specifying transformation rules and business logic. | bar: W7
10.2 | Design transformation logic to cleanse, validate, enrich, and aggregate data according to business requirements. | bar: W7
10.3 | Defining SCD and CDC as per data requirements​ | bar: W8
10.4 | Design ETL processes with scalability in mind to accommodate growing data volumes | bar: W8
Document data cleansing techniques, such as outlier detection, data deduplication, and data standardization procedures.​ | bar: W8
Ensure data quality and accuracy through data cleaning and validation processes.​ | bar: W8
7 | ETL Development and Implementation | bar: W7 to W9
11.1 | Developing pipelines for Batch load and implementing incremental/delta load logic on pipelines​ | bar: W7 to W9
11.2 | Developing Event hubs streams for streaming/near to real time data load while incorporating incremental/delta load logic on data streaming pipelines​ | bar: W7 to W9
11.3 | Testing and deploying the batch and streaming pipelines in repos | bar: W8 to W9
11.4 | Implementing SCD and CDC as per data requirements​ and develope framework. | bar: W8 to W9
11.5 | Developing Event hubs streams for streaming/near to real time data load while incorporating incremental/delta load logic on data streaming pipelines​ | bar: W8 to W9
8 | Data Quality and Validation | bar: W5 to W9
8.1 | Implementing the identified DQ rules, contraints, parameters and creating DQ and validation framework. | bar: W5 to W8
8.2 | Creating the necessary schema and one view table | bar: W6 to W7
8.3 | Working with sample table and synthetic data for testing the framework with wrong values | bar: W6 to W8
8.4 | Implementing error handling and notification rules | bar: W8 to W9
8.5 | Orchestrating the DQ framework by refactoring the pipelines | bar: W8 to W9
13 | Data Warehouse Development | bar: W8 to W18
Develop a migration plan and cut-over strategy, ensuring a smooth transition.​ | bar: W8 to W14
Delve into the intricacies of the source system, understanding data models, and the relationships between different data entities.​ | bar: W8 to W14
Evaluate the effectiveness of the current data modeling techniques and their alignment with business requirements.​ | bar: W8 to W14
Develop appropriate data models, ETL pipelines, data marts, and data lakes.​ | bar: W8 to W14
Optimize data processing pipelines to ensure efficient extraction, transformation, and loading (ETL) processes.​ | bar: W8 to W14
Conduct initial data validation from the old architecture to the new post-migration.​ | bar: W8 to W14
Implement a data migration approach with a parallel run and validate the migrated data. | bar: W8 to W14
Data modeling and incorporating business logics to gold datasets for consumption layer​ | bar: W8 to W14
13.2 | Ensuring data readiness to be consumed by data scientist and visualization experts ​ | bar: W14 to W15
13.3 | Implementing fabric best practices for the development model​ | bar: W14 to W18
14 | Data Governance (Data Quality, Profiling, Glossary) | bar: W11 to W14
Identify attribute definitions, entity relationships | bar: W11 to W12
Setup the purview governance across data estate, spanning both cloud and on-premises sources and establishing connectors to the identified sources | bar: W11 to W12
14.3 | Import glossary, create relationships within metadata and Associate glossary to metadata information | bar: W11 to W12
Adhere to data privacy regulations (e.g., GDPR, HIPAA) and industry standards.​ | bar: W11 to W12
Deploy robust data encryption algorithms and access control mechanisms to safeguard sensitive information. | bar: W11 to W12
Implementing enterprise data catalog, data governance, data security policies and access control matrix.​ | bar: W11 to W12
Include features for data lineage, audit trails, and metadata management.​ | bar: W11 to W12
14.4 | Create and run historical scans to discover metadata information in Azure Purview | bar: W12 to W14
14.5 | Building associations, relationships, defining collections and curating the scanning results | bar: W12 to W14
14.1 | Classifying data assets based on their sensitivity level, business criticality, and regulatory compliance requirements. | bar: W12 to W14
14.2 | Showcase notification and monitoring systems | bar: W12 to W14
15 | Data Management and Storage | bar: W11 to W13
Support multiple data formats (structured, semi-structured, unstructured) including tables, CSVs, JSON, XML, streaming data, and videos.​ | bar: W11 to W13
Ensure scalable storage capacity, easy-to-use data import/export features, data compression and encryption, access controls, audit trails, and data archival and backup.​ | bar: W11 to W13
Cataloging Metadata and Establishing a centralized repository or catalog serves as a single source of truth, where all metadata is stored and managed is essential. ​ | bar: W11 to W13
Regularly updating metadata, refreshing data assets, and retiring obsolete data assets ensure that the catalog remains accurate and up-to-date. | bar: W11 to W13
15 | Business Intelligence
15.1 | Requirement Gathering, KIP finalization & Access Enablement
15.1.1 | Requirement Gathering & Data understanding for Reporting Layer
15.1.2 | KPI Finalization & Signoff
15.2 | Power BI Report Wireframe, Development
15.2.1 | Wireframe Design & Sign-Off
15.2.2 | Data curation and abstraction & developing a data model as per the reporting use case
15.2.3 | Building Business Logics and related calculation for analysis
15.2.4 | Design & build report/dashboards for querying and visualizations
15.2.5 | Implement features as per the requirements
15.2.6 | Data Validation with test cases
16 | Azure DevOps Setup
16.1 | Creation of Azure DevOps Organization in a specific region
16.2 | Creation of Project and groups inside organization
16.5 | Initializing Repository inside Azure DevOps
16.1 | Configure Self-Hosted Agent in a Virtual Machine with required dependencies
16.11 | Installation of the required extension within the DevOps Portal for CI/CD utilization
17 | Azure Data Factory CI/CD
17.1 | Configuring service connection in Azure DevOps
17.2 | Attaching repository to ADF and commiting changes done by the developers.
17.3 | Configuring Ternary ADF for the deployment of SHIR if required
17.4 | Create Release pipeline
17.5 | Define deployment tasks inside release pipeline
17.6 | Configure override parameters for every linked services
17.7 | Configure pre-deployment approvals and post-deployment approvals
17.8 | Configure continuous deployment trigger
18 | Databricks CI/CD Pipeline
18.1 | Integrating databricks with github using PAT token of Databricks
18.2 | Create Build pipeline
18.3 | Create an artifact for further use
18.4 | Create Release pipeline
18.5 | Cleaning up the artifact
18.6 | Updating release pipeline security to define access
18.7 | Adding users for pre-deployment and post-deployment approvers
18.8 | Configure continuous deployment trigger
18.9 | Validating all the notebooks are deploying properly
19 | Logic Apps CI/CD
19.1 | Installing Visual Studio and related dependency on virtual machine
19.2 | Creating repository and attaching it to Azure repo.
19.3 | Creation of Build and release pipeline
19.4 | Cleaning up the artifact
19.5 | Updating release pipeline security to define access
19.6 | Configure pre-deployment approvals and post-deployment approvals
19.7 | Configure continuous deployment trigger
20 | PowerBI CI/CD
20.1 | Create workflow for copying files from PowerBI workspace to Sharepoint using Power Automate/ Logic Apps as per requirement
20.2 | Create storage account and blob container inside it to store reports
20.3 | Create workflow to copy files from Sharepoint to blob container using Logic Apps
20.4 | Create app registration using Azure AD
20.5 | Grant permission to app inside PowerBI workspace
20.6 | Create Build and release pipeline
20.7 | Cleaning up the artifact
20.8 | Updating release pipeline security to define access
20.9 | Configure pre-deployment approvals and post-deployment approvals
20.10 | Configure continuous deployment trigger
21 | Maintaining and Running CI/CD Pipelines | bar: W16 to W18
21.1 | Maintainin and Running CI/CD Pipeline for ADF, Databricks, Logic Apps, and Power BI | bar: W16 to W18
22 | SIT, Feedback Implementation & Go-Live
22.1 | SIT & Validation
22.2 | Additional Feature Implementation such as Email Subscription, RBAC etc.
22.3 | End to End process testing, sanity testing, model testing
22.4 | UAT Release & Feedback Implementation
23 | User Training and Documentation | bar: W16 to W18
24 | Deployment and Go-Live | bar: W16 to W18

## Project Planning 2 (hidden)
Milestone No. | SI.NO | Milestone Description | Task Owner | Dependency | Planned Start Date | Planned End Date | Duration(Days) | Actual Start Date | Actual End Date | Duration | Status | Comments
| 1 | Project Initiation and Requirements Gathering
| 1.1 | Onboarding of CT team in Sidra's infra and getting all the necessary accesses resolved
| 1.2 | Working with ADCCI's team to discover and define accurate data volume, connectivity towards sources.​
| 1.3 | Conducting sizing activity for Production, Development and Testing​
| 1.4 | Restructing and providing a approach for ETL ingestion and processing framework based on discovery​
| 1.5 | Defining business glossary alongside Bus and Identifying and modeling RBAC​
| 1.6 | Confirming the naming/coding standards to be followed in SIDRA's environment​
| 1.7 | Understand types of load per database per table and identify truncate/incremental logics as applicable​
| 1.8 | Define Unit testing strategy, User acceptance testing use-cases, analysis of success criteria and code acceptance parameters​
| 1.9 | Re-Defining the technical scope of work, if any change arise​
| 1.10 | Documenting the findings and observations and proposing the best possible approach if needed​
| 1.11 | Solution Design Review and Sign-off on discovery​
| 2 | Technical Discovery & Infrastructure PlanningTechnical Discovery & Infrastructure Planning
| 2.1 | Assess and Design
| 2.2 | Architecture Design And Review
| 2.3 | Discussion on Network Requirements and Connectivity Architecture
| 2.4 | Subscription Level Access
| 2.5 | Update Requirements and Design Document
| 2.6 | Solution Design Review And Sign-off
| 3 | Infrastructure Implementation- Develop And Deploy
| 3.1 | Hub (Centralized) Infrastructure setup
| 3.2 | Creation of Private DNS Zone for PaaS resources and Private endpoint (Browser Auth) for Databricks
| 3.3 | Creation of Transit Vnet for Browser Auth Databricks
| 3.4 | Setup the peering between hub and Transit virtual network
| 3.5 | Creation of Log Analytics workspace
| 4 | Develop And Deploy
| 4.1 | Spoke Dev Resource Deployment
| 4.1.2 | Procure IP address CIDR block tailored for EDP spoke
| 4.1.3 | Creation of IAC Script of Spoke Infrastrcuture
| 4.1.3 | Creation of the resource group
| 4.1.4 | Development and Deployment of the required networking components for the enviornment using IaC
| 4.1.5 | Development and Deployment of the required Azure PaaS services for the enviornment using IaC
| 4.1.6 | Deployment of the private endpoint for all the azure paas services using IaC
| 4.1.7 | Create and manage service principals or managed identities. (by Client)
| 4.1.8 | Creation of A records in Private DNS Zones in centralized location (Hub)
| 4.1.9 | Whitelisting of IP, Port and URLs on the Firewall (by Client)
| 4.1.10 | Configuration of SHIR,DSHA VM and installation of required softwares
| 4.1.11 | Assign RBAC roles to groups or users for specific resources
| 4.1.12 | Sanity testing of connectivity with data source and creating cluster in Azure Databricks workspace
| 4.1.13 | Creation of Linked Service for the data source
| 4.1.14 | Sanity Testing of the complete environment
| 4.1.15 | Perform integration testing to ensure proper communication and data flow between interconnected resources
| 5 | Spoke UAT Resource Deployment
| 5.1 | Procure Azure subscription specifically designated for deploying spoke resources
| 5.2 | Development of IaC scripts for required Azure resources
| 5.3 | Procure IP address CIDR block tailored for EDP spoke
| 5.4 | Creation of the resource group using the IaC scripts
| 5.5 | Deployment of the required networking components for the enviornment using IaC
| 5.6 | Deployment of the required Azure PaaS services for the enviornment using IaC
| 5.7 | Deployment of the private endpoint for all the azure paas services using IaC
| 5.8 | Create and manage service principals or managed identities. (by Client)
| 5.9 | Creation of A records in Private DNS Zones in centralized location (Hub)
| 5.10 | Whitelisting of IP, Port and URLs on the Firewall
| 5.11 | Configuration of SHIR,DSHA,on-prem Data Gateway VM and installation of required softwares
| 5.12 | Assign RBAC roles to groups or users for specific resources
| 5.13 | Sanity testing of connectivity with data source and creating cluster in Azure Databricks workspace
| 5.14 | Creation of Linked Service for the data source
| 5.15 | Sanity Testing of the complete environment
| 5.16 | Perform integration testing to ensure proper communication and data flow between interconnected resources
| 6 | Spoke Prod Resource Deployment
| 6.1 | Procure Azure subscription specifically designated for deploying spoke resources
| 6.2 | Development of IaC scripts for required Azure resources
| 6.3 | Procure IP address CIDR block tailored for EDP spoke
| 6.4 | Creation of the resource group using the IaC scripts
| 6.5 | Deployment of the required networking components for the enviornment using IaC
| 6.6 | Deployment of the required Azure PaaS services for the enviornment using IaC
| 6.7 | Deployment of the private endpoint for all the azure paas services using IaC
| 6.8 | Create and manage service principals or managed identities. (by Client)
| 6.9 | Creation of A records in Private DNS Zones in centralized location (Hub)
| 6.10 | Whitelisting of IP, Port and URLs on the Firewall
| 6.11 | Configuration of SHIR,DSHA,on-prem Data Gateway VM and installation of required softwares
| 6.12 | Assign RBAC roles to groups or users for specific resources
| 6.13 | Sanity testing of connectivity with data source and creating cluster in Azure Databricks workspace
| 6.14 | Creation of Linked Service for the data source
| 6.15 | Sanity Testing of the complete environment
| 6.16 | Perform integration testing to ensure proper communication and data flow between interconnected resources
| 7 | Security, Logging and Monitoring
| 7.1 | Configure the logging and monitoring of resources
| 7.2 | Setting up of Logging and Monitoring - Diagnostic Settings, Resource Health Alerts, Metric Alerts
| 7.4 | Enable Microsoft defender for continuous monitoring, threat detection, and security recommendations
| 7.5 | Configure Cost Management and Billing tools to monitor resource consumption
| 8 | Data Science & Analytics
Data Ingestion
| 8.1 | Data extraction
| 8.2 | Fetch data from data source
| 8.3 | Implement data quality checks & error handling
Data Extraction & Storing
| 8.4 | Define data extraction requirements and extract relevant data points.
| 8.5 | Extracting Text Using Azure Document Intelligence.
| 8.6 | Translate Arabic text to English and vice-versa
Enrich Data & Enable Search
| 8.7 | Create chunks for the text data
| 8.8 | Index data in Azure AI Search with the specified fields
| 8.9 | Create and Store Embeddings
| 8.10 | Create, train & update Indexer
OpenAI integration for Knowledge Mining, RFP Generation & Evaluation
| 8.11 | OpenAI integration for Knowledge Mining, RFP Generation & Evaluation
| 8.12 | Prompt optimization QnA Knowledge Mining, RFP Generation & Evaluation
| 8.13 | Context management and follow-up query
| 8.14 | Response formatting and Citation inclusion
| 8.15 | Summarization fine tuning for RFP generation
| 8.16 | GAP analysis & implementation
| 8.17 | Session management
| 8.18 | RFP generation in specified format
| 8.19 | RFP editing and saving
| 8.20 | Pre-Tender Clarification: Use of OpenAI model for answering questions from RFP
| 8.21 | Post-Tender Clarification: Prompt creation for analyzing the gap between submitted proposal and RFP
| 8.22 | Proposal Evaluation & Rating
| 8.23 | Report Generation
| 8.24 | ChatBot Development & Code implementation
Backend API Development
| 8.25 | Inference pipeline creation for QnA, RFP Generation and Evaluation
| 8.26 | Deployment & API Integration
| 8.27 | Inference pipeline integration and testing with UI
| 9 | ETL Process Design
| 9.1 | Map source data elements to target data structures, specifying transformation rules and business logic.
| 9.2 | Design transformation logic to cleanse, validate, enrich, and aggregate data according to business requirements.
| 9.3 | Defining SCD and CDC as per data requirements​
| 9.4 | Design ETL processes with scalability in mind to accommodate growing data volumes
| 10 | ETL Development and Implementation
| 10.1 | Developing pipelines for Batch load and implementing incremental/delta load logic on pipelines​
| 10.2 | Developing Event hubs streams for streaming/near to real time data load while incorporating incremental/delta load logic on data streaming pipelines​
| 10.3 | Testing and deploying the batch and streaming pipelines in repos
| 10.4 | Implementing SCD and CDC as per data requirements​
| 10.5 | Developing Event hubs streams for streaming/near to real time data load while incorporating incremental/delta load logic on data streaming pipelines​
| 11 | Data Quality and Validation
| 11.1 | Implementing the identified DQ rules, contraints, and parameters
| 11.2 | Creating the necessary schema and one view table
| 11.3 | Working with sample table and synthetic data for testing the framework with wrong values
| 11.4 | Implementing error handling and notification rules
| 11.5 | Orchestrating the DQ framework by refactoring the pipelines
| 12 | Data Warehouse Development
| 13.1 | Data modeling and incorporating business logics to gold datasets for consumption layer​
| 13.2 | Ensuring data readiness to be consumed by data scientist and visualization experts ​
| 13.3 | Implementing databricks best practices for the development model​
| 13.4 | Implementing enterprise data catalog, data governance, data security policies and access control matrix in Unity calatog​
| 13 | Data Governance (Data Quality, Profiling, Glossary)
| 14.1 | Data Scanning, Collections and Business Glossary Setup
| 14.1.1 | Identify attribute definitions, entity relationships
| 14.1.2 | Setup the purview governance across data estate, spanning both cloud and on-premises sources and establishing connectors to the identified sources
| 14.1.3 | Import glossary, create relationships within metadata and Associate glossary to metadata information
| 14.2 | Ingesting Metadata and implementation
| 14.2.1 | Create and run historical scans to discover metadata information in Azure Purview
| 14.2.2 | Building associations, relationships, defining collections and curating the scanning results
| 14.2.3 | Classifying data assets based on their sensitivity level, business criticality, and regulatory compliance requirements.
| 14.2.4 | Create incremental scans with time based and event based triggers
| 14.3 | Data Privacy
| 14.3.1 | creating policies for data retention, deletion, and access control
| 14.3.2 | Implementing data security policies and access control matrix
| 14.3.3 | Showcase notification and monitoring systems
| 14 | Business Intelligence
| 15.1 | Requirement Gathering, KIP finalization & Access Enablement
| 15.1.1 | Requirement Gathering & Data understanding for Reporting Layer
| 15.1.2 | KPI Finalization & Signoff
| 15.2 | Power BI Report Wireframe, Development
| 15.2.1 | Wireframe Design & Sign-Off
| 15.2.2 | Data curation and abstraction & developing a data model as per the reporting use case
| 15.2.3 | Building Business Logics and related calculation for analysis
| 15.2.4 | Design & build report/dashboards for querying and visualizations
| 15.2.5 | Implement features as per the requirements
| 15.2.6 | Data Validation with test cases
| 15 | Azure DevOps Setup
| 16.1 | Creation of Azure DevOps Organization in a specific region
| 16.2 | Creation of Project and groups inside organization
| 16.5 | Initializing Repository inside Azure DevOps
| 16.1 | Configure Self-Hosted Agent in a Virtual Machine with required dependencies
| 16.11 | Installation of the required extension within the DevOps Portal for CI/CD utilization
| 17 | Azure Data Factory CI/CD
| 18.1 | Configuring service connection in Azure DevOps
| 18.2 | Attaching repository to ADF and commiting changes done by the developers.
| 18.4 | Configuring Ternary ADF for the deployment of SHIR if required
| 18.6 | Create Release pipeline
| 18.8 | Define deployment tasks inside release pipeline
| 18.1 | Configure override parameters for every linked services
| 18.13 | Configure pre-deployment approvals and post-deployment approvals
| 18.14 | Configure continuous deployment trigger
Maintaining and Running CI/CD Pipelines
| 19 | Databricks CI/CD Pipeline
| 20.4 | Integrating databricks with github using PAT token of Databricks
| 20.5 | Create Build pipeline
| 20.7 | Create an artifact for further use
| 20.8 | Create Release pipeline
| 20.11 | Cleaning up the artifact
| 20.13 | Updating release pipeline security to define access
| 20.14 | Adding users for pre-deployment and post-deployment approvers
| 20.15 | Configure continuous deployment trigger
| 20.16 | Validating all the notebooks are deploying properly
Maintaining and Running CI/CD Pipelines
| 21 | Logic Apps CI/CD
| 22.1 | Installing Visual Studio and related dependency on virtual machine
| 22.3 | Creating repository and attaching it to Azure repo.
| 22.4 | Creation of Build and release pipeline
| 22.9 | Cleaning up the artifact
| 22.11 | Updating release pipeline security to define access
| 22.12 | Configure pre-deployment approvals and post-deployment approvals
| 22.13 | Configure continuous deployment trigger
Maintaining and Running CI/CD Pipelines
| 23 | PowerBI CI/CD
| 24.1 | Create workflow for copying files from PowerBI workspace to Sharepoint using Power Automate/ Logic Apps as per requirement
| 24.2 | Create storage account and blob container inside it to store reports
| 24.4 | Create workflow to copy files from Sharepoint to blob container using Logic Apps
| 24.5 | Create app registration using Azure AD
| 24.6 | Grant permission to app inside PowerBI workspace
| 24.7 | Create Build and release pipeline
| 24.13 | Cleaning up the artifact
| 24.16 | Updating release pipeline security to define access
| 24.17 | Configure pre-deployment approvals and post-deployment approvals
| 24.18 | Configure continuous deployment trigger
| 24.2 | Maintaining and Running CI/CD Pipelines
| 24 | SIT, Feedback Implementation & Go-Live
| 16.1 | SIT & Validation
| 16.2 | Additional Feature Implementation such as Email Subscription, RBAC etc.
| 16.3 | End to End process testing, sanity testing, model testing
| 16.4 | UAT Release & Feedback Implementation
| 25 | User Training and Documentation
| 26 | Deployment and Go-Live

## Resource Matrix (hidden)
Sr No | Resources | Count | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | Total Hours
1 | Project Manager | 1 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 320
2 | Business Analyst | 1 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 160
3 | Cloud Architect | 1 | 10 | 20 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 130
4 | Infra Engineer | 2 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 340
5 | Automation Engineer | 2 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 560
6 | Solution Architect | 1 | 0 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 100
7 | Data scientist | 2 | 0 | 10 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 1140
8 | Data Engineering | 2 | 0 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 10 | 10 | 10 | 1020
9 | Data Integration Engineer | 2 | 0 | 10 | 10 | 10 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380
10 | Sr Data Engineer | 1 | 0 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 280
11 | Data Governance Engineer | 1 | 0 | 40 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200
12 | Power BI Developer | 2 | 0 | 0 | 0 | 10 | 20 | 20 | 20 | 20 | 40 | 40 | 40 | 40 | 20 | 20 | 10 | 10 | 10 | 640
13 | DevOps Engineer | 1 | 0 | 0 | 0 | 10 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 330
Total |  | 19 | 20 | 210 | 210 | 230 | 300 | 345 | 345 | 300 | 280 | 210 | 210 | 200 | 180 | 150 | 130 | 110 | 130 | 5600